## Sheet1
Affected area | Start Date | Finish Date | Works
Discovery Lane carparks | 2021-11-03 | 2021-12-03 | Discovery Lane carparks on right hand side.
Banksia (1016) loading dock entry laneway | 2021-11-03 | 2021-11-09 | Entry to loading dock will remain open.
Carpark: P3 | 2021-11-03 | 2021-11-12 | Whole carpark will be closed.
Carpark: P1 | 2021-11-08 | 2021-11-18 | Gate 4 closure. .Entry will be via gate 3A and then turn right through cark P1. Temporary signage will be placed on the new entry gate.
Pandanus (1022) carpark West | 2021-11-08 | 2021-11-25 | Pandanus (1022) carpark West will be closed Links loop will remain open during work.
Links Loop (behind Pandanus building) | 2021-11-08 | 2021-11-25 | Repairs to bitumen road on Links Loop (behind Pandanus building). Links loop will remain open during work. Carparks will be closed to allow access
Walkway from Dianella to Cycad | 2021-11-11 | 2021-11-16 | Walkway from Dianella to Cycad level 2. Walkway will remain open