## Sheet1
Compressed Air and Vacuum Services December Schedule
Area / Campus | Building Name | Building number | Start Date | Finish Date | Times
P4 | Ritchie Labs Roof Plant Room | 64A | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | Ritchie Labs Roof Plant Room | 64A | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | CAI Level 6 Plant room | 57 | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | CAI Level 6 Plant room | 57 | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
Remote Sites | Behind Workshop | 632 | 2021-12-14 | 2021-12-14 | 12pm - 3pm | PRECICNT 2 | P2
P2 | Hartley Teakle | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm | PRECINCT 3 | P3
P2 | Hartley-Teakle N01 | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm | PRECINCT 4 | P4
P2 | Hartley-Teakle N02 | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm | GATTON | G
P3 | John Hines | 62 | 15/12/2021 | 15/12/2021 | 12pm - 3pm | REMOTE SITES | RS
P3 | Zelman Cowan | 51 | 15/12/2021 | 15/12/2021 | 12pm - 3pm | LONG POCKET | LP
P4 | Molecular Biosciences(roof) | 76 | 15/12/2021 | 15/12/2021 | 12pm - 3pm | CARRY OVER |  | RESCHEDULED
P4 | Molecular Biosciences (roof) | 76 | 15/12/2021 | 15/12/2021 | 12pm - 3pm
Gatton | Blacksmiths | 8208 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Industries | 8111 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Industries | 8111 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Protection | 8107 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | SOVSCSB | 8179 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | SOVSCSB | 8179 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | Animal Studies | 8150 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | Animal Studies | 8150 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Long Pocket | Pandanus | 108? | 2021-12-20 | 2021-12-20 | 12pm - 3pm
Long Pocket | Glasshouse West 1017 A | 1017A | 2021-12-20 | 2021-12-20 | 12pm - 3pm
Long Pocket | Banksia Bld ( Level 2 ) |  | 2021-12-20 | 2021-12-20 | 12pm - 3pm
P2 | Parnell Outside shed | 7 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P2 | PARNELL | 5 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P4 | Chem 68 Roof p/room | 68 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P4 | Chem 68 Roof p/room | 68 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | Dayboro Vet Hospital | 793 | 21/12/2021 | 21/12/2021 | 7:30am - 12pm
Remote Sites | Dayboro Vet Hospital | 793 | 21/12/2021 | 21/12/2021 | 7:30am - 12pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | Oral Health | 883 | 21/12/2021 | 21/12/2021 | 12pm - 3pm

## Sheet2
P4 | Ritchie Labs Roof Plant Room | 64A | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | Ritchie Labs Roof Plant Room | 64A | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | CAI Level 6 Plant room | 57 | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
P4 | CAI Level 6 Plant room | 57 | 2021-12-14 | 2021-12-14 | 7:30am - 12pm
Remote Sites | Behind Workshop | 632 | 2021-12-14 | 2021-12-14 | 12pm - 3pm
P2 | Hartley Teakle | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm
P2 | Hartley-Teakle N01 | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm
P2 | Hartley-Teakle N02 | 83 | 15/12/2021 | 15/12/2021 | 7:30am - 12pm
P3 | John Hines | 62 | 15/12/2021 | 15/12/2021 | 12pm - 3pm
P3 | Zelman Cowan | 51 | 15/12/2021 | 15/12/2021 | 12pm - 3pm
P4 | Molecular Biosciences(roof) | 76 | 15/12/2021 | 15/12/2021 | 12pm - 3pm
P4 | Molecular Biosciences (roof) | 76 | 15/12/2021 | 15/12/2021 | 12pm - 3pm
Gatton | Blacksmiths | 8208 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Industries | 8111 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Industries | 8111 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | Plant Protection | 8107 | 2021-12-16 | 2021-12-16 | 7:30am - 12pm
Gatton | SOVSCSB | 8179 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | SOVSCSB | 8179 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | Animal Studies | 8150 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Gatton | Animal Studies | 8150 | 2021-12-16 | 2021-12-16 | 12pm - 3pm
Long Pocket | Pandanus | 108? | 2021-12-20 | 2021-12-20 | 12pm - 3pm
Long Pocket | Glasshouse West 1017 A | 1017A | 2021-12-20 | 2021-12-20 | 12pm - 3pm
Long Pocket | Banksia Bld ( Level 2 ) |  | 2021-12-20 | 2021-12-20 | 12pm - 3pm
P2 | Parnell Outside shed | 7 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P2 | PARNELL | 5 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P4 | Chem 68 Roof p/room | 68 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
P4 | Chem 68 Roof p/room | 68 | 2021-12-20 | 2021-12-20 | 7:30am - 12pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | Dayboro Vet Hospital | 793 | 21/12/2021 | 21/12/2021 | 7:30am - 12pm
Remote Sites | Dayboro Vet Hospital | 793 | 21/12/2021 | 21/12/2021 | 7:30am - 12pm
Remote Sites | RBWH Block 6 | 910 | 21/12/2021 | 21/12/2021 | 12pm - 3pm
Remote Sites | Oral Health | 883 | 21/12/2021 | 21/12/2021 | 12pm - 3pm