## Sheet1
Campus | Building Name | Building Number | Room Number (If applicable) | Start Date | Finish Date | Start Time (am/pm) | Finish Time (am/pm) | Disruption / Works type | Additional Notes
St Lucia | Sir Llew Edwards Building | 14 | All | 2022-05-06 | 2022-05-06 | 6:30am | 7:00am | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 0.5 hour during this time. Fire doors may close during test. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Colin Clark | 39 | ALL | 2022-05-06 | 2022-05-06 | 7:00am | 12:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Properties And Facilities | 87 | ALL | 2022-05-06 | 2022-05-06 | 12:00pm | 2:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Don Nicklin Building | 10074 | ALL | 2022-05-09 | 2022-05-09 | 7:00am | 12:00PM | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Axon Building | 10047 | ALL | 2022-05-09 | 2022-05-09 | 7:00am | 12:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Sir James Foots Building | 10047A | ALL | 2022-05-09 | 2022-05-09 | 7:00am | 14:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Mansergh Shaw Building | 45 | ALL | 2022-05-09 | 2022-05-09 | 12:00pm | 2:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Sir William Macgregor Building | 64 | ALL | 2022-05-10 | 2022-05-10 | 7:00am | 10:00am | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Cumbrae-Stewart Building | 72 | ALL | 2022-05-10 | 2022-05-10 | 10:00am | 12:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Connell Building | 26 | ALL | 2022-05-11 | 2022-05-11 | 7:00am | 1:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Human Movement Studies Buildin | 26b | ALL | 2022-05-11 | 2022-05-11 | 7:00am | 1:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Human Performance Laboratories | 26a | ALL | 2022-05-11 | 2022-05-11 | 7:00am | 1:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Biological Sciences Library | 94 | ALL | 2022-05-12 | 2022-05-12 | 11:00am | 2:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Parnell Building | 7 | ALL | 2022-05-12 | 2022-05-12 | 6:30am | 9:00am | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Therapies Annexe | 84a | ALL | 2022-05-12 | 2022-05-12 | 8:00am | 12:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.
St Lucia | Therapies Building | 84 | ALL | 2022-05-12 | 2022-05-12 | 8:00am | 12:00pm | fire/HVAC/Fire doors | The Design of the Air Condition system is to stop during a fire alarm. Technicians will need to inspect the units to ensure they act as designed. The systems should only be off for a maximum of 1 hour during this time. Aditional fans may start during this time. Fire doors may close during test. The impact will be minimal. The system will return to normal after testing. There will be no tones during tests.